Implementation of Cold Chain Equipment Optimization Platform
TechNet 2017
Implementation of Cold Chain Equipment Optimization Platform
Sept 2017
UNICEF Supply Division - HTC – Cold Chain Technical Unit July 21 , 2017

---
Outline
Introduction
CCEOP application and implementation at a glance
Application and implementation status
Procurement Process
Experiences so far; potential challenges
CCEOP success factor
[Speaker Notes: Add establish PMT]

---
The CCEOP aims to better protect vaccine potency in-country
The CCEOP aims to better protect vaccine potency in-country
Over the next 5 years, ~150,000 optimal refrigerators will be procured and deployed, as well as freeze-free cold boxes and vaccine carriers
Optimal products, to better protect vaccine potency
“Grade A" freeze protection
Extended ambient temperature range
Bundled voltage stabilizers
Bundled temperature monitors
+
“Service bundle”, to deploy CCE more quickly and reliably
Suppliers are accountable for in-country distribution, installation, and training of end-users at facilities
MOH is responsible for customs clearance`
ILR
SDD
Freeze-free cold boxes, vaccine carriers
Long-term passive devices

---
Service delivery is the responsibility of manufacturers through local service providers
Overall paradigm shift with inclusion of service bundle approach.
From technical standard to Project Management skills
Kenya Local Service Partner
UNICEF
Supplier
Country
Uganda Local Service Partner
Gavi
Haiti Local Service Partner
Equipment Purchase Order + Service Bundle Contract
Funding
Sub-contract in countries
Stakeholders involved in successful service delivery
Supplier
Freight Forwarder
MoH
Supplier via Service Provider
Supplier via Service Provider
Monitored, facilitated by in-country PMT + UNICEF SD
Delivery to supplier port
International freight
Customs clearance
Local distribution & warehousing
Installation, end-user training, commissioning

---
CCE OP application & implementation process at a glance
Activities
Status check
A
CCEOP
Application & Approval
WHO Pre-Review
IRC Review
Gavi Board Approval
Gavi issues Decision Letter to country
Gavi issues Authorization Schedule to UNICEF SD
B
Procurement Planning
MoH to send UNICEF SD an Operational Deployment Plan
UNICEF SD issues tender for service bundle & develops a costed operational plan
Gavi to approve costed operational plan
MoH to agree on costed operational plan
UNICEF SD to Cost Estimate (CE) to MoH
MoH accepts CE and transfers country joint-investment share to UNICEF SD
Gavi transfers joint-investment share to UNICEF SD
C
Procurement
SD to place purchase orders
SD to contract local vendor for third party post inspection
SD/CO to track delivery & installation
CO to certify invoices & send for payment
Completed
Ongoing
Status check color code :
[Speaker Notes: Add establish PMT]

---
CCE OP application & implementation at a glance
GAVI Process
# of CCEOP eligible countries	55
Decision letter issued	13 ( as of October 2017)
Decision letter in process	8 ( as of October 2017)
UNICEF-SD Process
SD issuing country specific service bundle tenders in Q4/2017
15-20 tenders are expected through the system in the coming months.
[Speaker Notes: Add establish PMT]

---
Procurement process at a glance
Preparation part
Long Term Arrangement (LTA) for higher performing CCE
Pre qualifying suppliers for service bundle
Implementation part (Country specific)
Confirmation of Operational Deployment Plan
Preparation of Terms of Reference
RFPS issuance (Tender)
Review and evaluation process (Tenders)
Development of Costed Operational Plan ( Government and GAVI review)
UNICEF-Contract Review Committee process
Issuance of CE including country and Gavi funding release
PO placement
[Speaker Notes: Add establish PMT]

---
Experiences so far
Experiences so far
Application, DL and ODP requirement
Countries are expected to identify three different manufacturer preferences by volume category.
As per GAVI guidelines, UNICEF tender invitations have reflected these country preferences
Experience so far
Importance of Health Facility assessment (ODP)
Tendency that countries focus on a few manufacturers
Complexity of custom clearance process including tax waiver
Lack of involvement of Supply & Logistics staff in supporting process
CCEOP service bundling can be challenging in some countries
[Speaker Notes: One Health Facility assigned with both SDD and Mains Powered Refrigerators (ILR) One Health Facility assigned with multiple refrigerators (up to 30) Health Facilities with straw roofing are identified as “ fit for solar panel roof mounting” Health facility without electricity supply is assigned Mains Powered Refrigerator Health Facility with electricity supply is assigned with solar South Sudan example 30 – 40 % of refrigerators deliveries require chartered flight. Convoy should be used to distribute equipment for the majority of rest of locations Any supply to be delivered ex-Juba to field locations should be cleared – this clearance process involves RRC ( Relieve and Rehabilitation commission) Joint Border verification Monitoring Ministry of Defense]

---
CCEOP Project Management – What does it entail
CCEOP Project Management – What does it entail
Application phase
CCE inventory / HF Segmentation / Strategic deployment plan / (15 mandatory documents)
Preparation for implementation (ODP)
HF readiness / Detailed distribution plan / Development of deviation protocol / Stake holder mapping / Risk mapping
Implementation
Custom clearance / Tracking / Advocacy / communication / Managing deviations / Communication with service provider / Documenting lessons learnt
Monitoring and Evaluation
PMT should oversee the entire implementation

---
CCE OP success factors
Country Project Management Team under leadership of MOH is key to ensure success
Institutionalize PMT and allocate sufficient resources (funding & man power)
PMT members should include stakeholder
Development of ODP is primarily the responsibility of MoH through PMT.
Health Facility Readiness should be prioritized
ODP is the early indications on country ownership + indication where we can foresee implementation challenges
[Speaker Notes: Add establish PMT]

---
Thank you
Thank you