## Instructions
Instructions for adapting and using the template workplan
1) | Update the timeline ( year and month) of the workplan to best suit country schedule/context. E.g. If the activities began in May 2017, then the workplan can be modified to begin from the month of May in 2017.
2) | Adapt the suggested activities according to your specific planning needs
Note: high level activities existing in workplan template should remain, however TWG may choose to include additional activities from the "suggested sub activities tab" to build out as necessary and create a more detailed workplan
3) | Determine how much time each activity will require to complete (from start of sub activities to completion); and what firm deadlines (e.g. launch) may occur -- which should influence start dates of activities
4) | Mark time periods (green bars) and critical deadlines (red diamond) for relevant major activities (e.g. Launch date) in the workplan according to needed time and deadlines from step 2
5) | Assign a "responsible" individual within EPI and technical partner to follow up on execution of each task.
6) | If applicable, specify any deliverables (e.g. reports or products) that should be produced by the end of the activity in Column F
7) | At the beginning of each meeting, use the "Status" column (Column B) to check and note progress with the dropdown menu (e.g. "Complete", "On track", "Action required", "Critical delay" or "Not Started").
Edit Dropdown Options
Please edit the dropdown options by adding or changing only information in blue cells
Status
Complete
On track
Action required
Critical delay
Not yet started

## Template Workplan
NVI Operational Workplan Template | [5 empty] | Key
- Recommended amount of time to budget
- Firm deadlines (e.g. Launch date)
[6 empty] | Year 1 : xxxx |  | 2017 | [9 empty] | Year 2 : XXXX |  | 2018
| Status | Activity | EPI responsible | Technical Partner | Comments or deliverables | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
| Action required | Planning for HPV introduction
| On track | Revitalize and develop schedule of TWG meetings for HPV | MOHCC | WHO | Schedule and minutes of the TWG | bar: 2017 Dec to Year 2 : XXXX Jan; 2018 Mar to 2018 May
| Critical delay | Planning for timelines of sensitization for new stakeholders | MOHCC/JSI | WHO | Timelines developed | bar: Year 2 : XXXX Jan
| Not yet started | Update operational plan and budget (e.g. for new cohort phasing) and share with Gavi | MOHCC/JSI | UNICEF | Updated plan | bar: 2017 Dec to Year 2 : XXXX Jan
| Not yet started | Communicate operational plan and budget to sub-national levels | MOHCC/JSI | JSI/WHO | Communicated budgeted operational plan | bar: 2017 Dec to Year 2 : XXXX Jan
| Not yet started | Manage fund disbursement up to sub-national levels (e.g. VIG funds for training) | Accountant | UNICEF | Funds disbursed to Provinces and Districts | bar: 2017 Dec to Year 2 : XXXX Jan
| Not yet started | Communicate with subnational levels to ensure engagement of education sector | MOHCC/JSI | WHO/JSI | Education Sector engaged at all leves | bar: 2017 Dec to Year 2 : XXXX Jan
| Not yet started | Subnational: establish linkages with education officials and schools as relevant | MOHCC/JSI | JSI/WHO | Education officials and linked with | bar: Year 2 : XXXX Jan to Year 2 : XXXX Feb
| Not yet started | Subnational: Develop detailed microplan introduction activities and share with national | MOHCC/JSI | JSI/WHO | Micro plans developed | bar: Year 2 : XXXX Jan to Year 2 : XXXX Feb
| Not yet started | Subnational: Microplan activities carried out in time for introduction | MOHCC/JSI | JSI/WHO | Updated micro plans activities | bar: Year 2 : XXXX Jan to 2018 Mar
| Not yet started | Secure Vaccine Supply/Cold Chain
| Not yet started | Review cold chain readiness at all levels to identify gaps and develop mitigation | MOHCC | WHO | Cold chain readiness reviewed at levels | bar: Year 2 : XXXX Jan
| Not yet started | Place vaccines order (factor in shipment time) | MOHCC | UNICEF | Vaccine ordering carried out | bar: 2017 Sep
| Not yet started | Clear vaccine supply from customs | MOHCC | UNICEF | Cleared vaccines from customs | bar: Year 2 : XXXX Jan
| Not yet started | Forecast vaccine need for subnational level and bundle supplies | MOHCC | WHO | Vaccine forecasting done | bar: 2018 Apr
| Not yet started | Distribution of materials to subnational and HF level
| Not yet started | Updating of data tools (including printing) | MOHCC | UNICEF/JSI | Updated data tools printed | bar: 2017 Dec
| Not yet started | Update distribution plan (data tools, soc mob materials, vaccine), as relevant | MOHCC/JSI | UNICEF/JSI | Distribution plan updated | bar: Year 2 : XXXX Jan
| Not yet started | Transport vaccine and immunisation materials to district | MOHCC | WHO/JSI | Vaccine and immunisation material distributed | bar: Year 2 : XXXX Feb
| Not yet started | Distribute updated immunization tools to districts | MOHCC/JSI | WHO | Updated immunisation tools distributed | bar: Year 2 : XXXX Feb
| Not yet started | Training
| Not yet started | Develop training plan, materials, and print materials | MOHCC/JSI | WHO/JSI | Trainig plan,materials developed and printed | bar: Year 2 : XXXX Jan to Year 2 : XXXX Feb
| Not yet started | Conduct national level TOT | MOHCC/JSI | WHO/JSI | National level TOT Conducted | bar: Year 2 : XXXX Jan to Year 2 : XXXX Feb
| Not yet started | Implement training strategy (e.g. subnational trainings) | MOHCC/WHO/JSI | WHO/JSI | Sub national levels trained | bar: Year 2 : XXXX Feb to 2018 Apr
| Not yet started | Social Mobilization
| Not yet started | Develop social mobilization strategy with all relevant stakeholders (e.g. adolescent CSOs) | MOHCC/JSI | JSI/UNICEF | Social mobilisationstrategies developed | bar: Year 2 : XXXX Feb
| Not yet started | Print and distribute social mobilization materials | MOHCC/JSI | JSI/UNICEF | Materials distributed | bar: Year 2 : XXXX Feb
| Not yet started | Implement communication strategy | MOHCC/JSI | JSI | Communication strategy implemented | bar: Year 2 : XXXX Feb
| Not yet started | Plan for and carry out national level launch event (and subnational level) | MOHCC/J/WHO | WHO/JSI | National launch planned and carried out | bar: 2018 Apr
| Not yet started | Hold HPV assessment activities
| Not yet started | Carry out district level readiness assessment (3 and 1 month prior to introduction) | MOHCC/JSI/WHOWHO | WHO/JSI | District readiness assesment carried out | bar: Year 2 : XXXX Feb; 2018 Apr
| Not yet started | Hold post launch assessment (2-6 weeks post introduction) | MOHCC/JSI/WHOWHO | WHO/JSI | Post launch assessment done | bar: 2018 Jun
| Not yet started | Review HPV coverage data (monthly or as relevant for campaign delivery) | MOHCC/JSI/WHOJSI-GAVI | WHO/JSI | HPV coverage data reviewed | bar: 2018 Jun to 2018 Dec
| Not yet started | Plan and implement HPV PIE (timing in line with delivery model) | MOHCC/WHO/WHO | WHO | PIE planned and carried out | bar: 2018 Nov

## Suggested sub activities
|  |  | Responsibility | Partner | Deliverables
Planning for HPV introduction | [5 empty] | JANUARY |  |  |  | FEBRUARY |  |  |  | MARCH |  |  |  | APRIL |  |  |  | MAY
[6 empty] | wk1 | wk2 | wk3 | wk4 | wk1 | wk2 | wk3 | wk4 | wk1 | wk2 | wk3 | wk4 | wk1 | wk2 | wk3 | wk4 | wk1 | wk2 | wk3 | wk4
Update operational plan and budget
| Review existing operational plan and budget by sub-committees |  | MOHCC &MoPSE | UNICEF,WHO &JSI | Operational plans and budget reviewed and communicated to subnational levels | bar: JANUARY wk2
|  | Resource mobilisation, | EPI Manager, PD/PSNE | UNICEF,WHO &JSI ,ICC, Technical Committee | bar: JANUARY wk1
|  | Advocacy, Publicity, Communication and Crisis Management | Health Promotion Manager Director ICT MoPSE | UNICEF,WHO,JSI,CSOs(NANGO, ZNCWC), MoPSE, Youth and Women, Lions Club,World Vision, Rotarians, Telecoms | bar: FEBRUARY wk1 to FEBRUARY wk2
|  | Waste Management | Manager Waste Management | UNICEF,WHO &JSI | bar: FEBRUARY wk1 to FEBRUARY wk2
|  | Surveillance | EPI Manager | WHO &JSI | bar: FEBRUARY wk1 to FEBRUARY wk2
|  | Vaccine Management and Logistics | EPI Logistician | UNICEF,WHO , JSI &MCAZ | bar: FEBRUARY wk1 to FEBRUARY wk2
Sensitization of new stakeholders
| Identify and engage new stakeholders e.g Portifolio Committee on Health and Child Care, Econet, Telecel, Netone, Media, CSOs targeted towards adolescents/children |  | EPI Manager | UNICEF,WHO &JSI& CSOs | Stakeholders identified and engaged | bar: FEBRUARY wk1 to FEBRUARY wk2
| Hold sensitization meetings with school health coordinators and stakeholders to identify new links |  | EPI Manager, PD/PSNE | UNICEF,WHO &JSI | School health coordinators and stakeholders sensitized | bar: FEBRUARY wk1 to FEBRUARY wk2
Social mobilization
| Finalisation of social mobilization strategy/plan |  | Health Promotion Manager Director ICT MoPSE | UNICEF,WHO,JSI,CSOs,NANGO,ZNCWC,Youth and Women,ACCZ, UDACIZA | Finalised social mobilization strategy | bar: FEBRUARY wk2 to FEBRUARY wk3
| Distribute finalised strategy/plan |  |  |  | Strategy/Plan distributed | bar: FEBRUARY wk1 to FEBRUARY wk2
| Printing and production of flighting material for social mobilization (e.g. FAQs, Key Messages, Fact Sheets, posters, radio spots, etc.) |  |  |  | Printed Social mobilization materials and continuous fighting radio spots | bar: FEBRUARY wk3 to FEBRUARY wk4
Flighting of radio/sms and TV spot | bar: MARCH wk1 to MAY wk4
| Appraise Crisis Communication Committee (CCC) (AEFI handling, myth and misconceptions) |  |  |  | CCC appraised | bar: JANUARY wk3 to JANUARY wk4
| Implementation of social mobilisation activities at sub national levels) |  |  |  | Communication strategy implemented | bar: MARCH wk1 to MAY wk4
Manage fund disbursement to subnational levels
| Follow up funds |  | EPI Manager | UNICEF | Evidence of Correspondence | bar: JANUARY wk3 to JANUARY wk4
| Distribute funds for subnational activities |  | EPI Manager | UNICEF | Funds disbursed to Subnational level | bar: FEBRUARY wk3 to FEBRUARY wk4
Collaborate with MoPSE on HPV vaccination support in schools
| Conduct planning meetings at national with MoPSE on HPV activities and potential areas of support for HPV activities |  | EPI Manager | UNICEF,WHO &JSI | MoPSE linked with on HPV activities | bar: JANUARY wk2 to JANUARY wk3
| Subnational: conduct planning meetings with schools for HPV support and sensitization of district and school officials |  | PD/PSNE | UNICEF,WHO &JSI | Linkages with schools developed | bar: FEBRUARY wk2
| Communication to MoPSE and PMDs on roll out of HPV |  | EPI Manager | bar: JANUARY wk4
| Send out communication to School Heads |  | PD/PSNE | UNICEF,WHO &JSI | Communication to School Heads carried out | bar: FEBRUARY wk1
| Development of relevant timeline for School Heads and teacher sensitization |  | PD/PSNE | UNICEF,WHO &JSI | Timeline for sensitization developed | bar: FEBRUARY wk1
| Mapping and registration of out of school girls |  | EPI Manager | bar: FEBRUARY wk1
| Registration of eligible girls in schools |  | PD/PSNE | UNICEF,WHO &JSI | Vaccination systems developed | bar: FEBRUARY wk1
Subnational: Microplanning activities
| Finalisation of micro plans |  | EPI Manager | UNICEF,WHO &JSI | Reports of visits | bar: APRIL wk2 to APRIL wk4
| Pre implementation supervision at health facility level |  | EPI Manager | UNICEF,WHO &JSI | Reports of visits | bar: APRIL wk3 to MAY wk2
| Integrate HPV into regular supportive supervision and refresher trainings |  | EPI Manager | UNICEF,WHO &JSI | HPV integrated into regular supportive supervision
Secure vaccine supply
| Receipt of Vaccine and Supplies |  | EPI Logistician | UNICEF,WHO &JSI | Availability of vaccines | bar: FEBRUARY wk1 to FEBRUARY wk2
| Distribution of vaccines and supplies |  | EPI Logistician | UNICEF,WHO &JSI | Vaccines distributed | bar: MARCH wk1 to MARCH wk3
Data tools
| Adapt existing reporting system to integrate/add HPV (e.g. HMIS/DHIS, registers, tally sheets, etc.) |  | DD Health Information | UNICEF,WHO &JSI | HPV integrated into routine system | bar: MARCH wk1 to MARCH wk3
| Review vaccination cards with HPV facts and clear HPV reminder |  | EPI Manager | UNICEF,WHO &JSI | Vaccination cards reviewed | bar: JANUARY wk2 to JANUARY wk3
| Print tools |  | EPI Manager | UNICEF | Printed tools | bar: FEBRUARY wk3 to FEBRUARY wk4
Training
| Updating training materials |  | EPI Manager | UNICEF,WHO &JSI | Updated training materials | bar: JANUARY wk2 to JANUARY wk4
| Update immunization guidelines and protocols e.g. job aides |  | EPI Manager | UNICEF,WHO &JSI | Updated immunization guideline | bar: JANUARY wk2 to JANUARY wk3
| Orientation of media houses on HPV introduction |  | Health Promotion Manager | UNICEF,WHO &JSI | Media houses oriented | bar: FEBRUARY wk4
| Recruitment and training of independent monitors |  | EPI Manager | UNICEF,WHO &JSI | Reports of Independent monitors trained | bar: APRIL wk4 to MAY wk2
| Distribution of training materials |  | EPI Manager | UNICEF | Printed training materials | bar: MARCH wk1 to MARCH wk3
| Hold training of trainers (TOT) National Level |  | EPI Manager | UNICEF,WHO &JSI | TOT Report, distribution list of HPV materials | bar: MARCH wk1 to MARCH wk2
| Training of health workers and school health coordinators on HPV vaccine introduction |  | EPI Manager | UNICEF,WHO &JSI | HPV delivery model, schedule ,eligibility clarified to districts | bar: APRIL wk4 to MAY wk2
HPV introduction assessments
| Distribution of HPV stickers |  | EPI Logistician | UNICEF,WHO &JSI | Stickers distributed | bar: FEBRUARY wk1 to FEBRUARY wk2
| National Level readiness assessments |  | EPI Manager, PD/PSNE | UNICEF,WHO &JSI | Readiness assessment report | bar: MARCH wk1 to MARCH wk4
| Plan launch ceremony |  | EPI Manager, PD/PSNE | UNICEF,WHO &JSI | Launch plan available | bar: APRIL wk3 to MAY wk2
| Conduct HPV Launch Event |  | EPI Manager, PD/PSNE | UNICEF,WHO &JSI | Launch event report | bar: MAY wk3
| National roll out of HPV vaccination |  | EPI Manager, PD/PSNE | UNICEF,WHO &JSI | HPV Coverage report | bar: MAY wk3
| Mop Up Activities |  | EPI Manager, PD/PSNE | UNICEF,WHO &JSI | HPV Coverage report | bar: MAY wk3 to MAY wk4
| Supportive supervision during HPV roll out |  | EPI Manager, PD/PSNE | UNICEF,WHO &JSI | Supportive Supervision report | bar: MAY wk3 to MAY wk4
| Conduct PIE after 6 months |  | EPI Manager | UNICEF,WHO &JSI | PIE data collection conducted
Funds Available
No Funds for Activity