## Slide 1: NIGERIA: COVID-19 Operation
Learnings and Best Practices

## Slide 2
35 Branches
Supported by
  IFRC
  ICRC
  BRC
  NRC
  GRC
  Novarits
Volunteers: 1,390
Staff: 153
June 2020 - December 2021

## Slide 3
Intervention pillars
Donation of PPE Treatment Centres
5 Branches
11,456,090
RCCE
162,857
PSS
17,721
Contact Tracing
IPC:
Ambulance services
Health facilities, orphanages
840 Hand Washing Stations
Safe burials and supportive referrals
2m
COVID-19 Vaccination campaign
10,625,615

## Slide 4
Implementation Strategies
House to House sensitization and social mobilization
Street campaign (Road walk)
Live call-in Radio show
Psychological First Aid for vaccine hesitancy
COVID-19 VACCINATION

## Slide 5
Success Stories
465, 131 persons reached through house-to-house awareness (between October & December 2021)
445, 239 registered and took the vaccine with the help of RC volunteers
191, 248 persons reached with PFA for vaccine hesitancy
10,625,615 reached through call -in radio shows
Recognition by Government and other partners; and willingness to work with the RC
Increased membership drive and visibility

## Slide 6
Blockages to COVID-19 vaccination
Infodemic on COVID-19 vaccines
Lack of public trust in Government
Lack of funding to reach the underserved/hard to reach population
Poor follow -up system
Misconceptions around the use of different vaccines
Conflicts and insecurity

## Slide 7
Recommendations
A holistic and timely planning, fast execution of plans
Rigorous community involvement, and a robust multi-sectoral approach
Establish follow - up system for subsequent doses
RC volunteers to support registration of beneficiaries